# Forest Harvesting Effects on

# Eastern Oregon Mass Wasting:

# Rapid Systematic Literature Review Project

# 2026

# Request for Proposals

Announcement Date: Monday, February 23, 2026, 10:00 am Pacific Time

Full Proposals Due: Monday, March 23, 2026, before 11:59 pm Pacific Time

Late and/or incomplete applications will not be considered.

Individual Requests: Not to exceed $80,000

Anticipated Funding: 1 project, Total approx. $80,000

Project Duration: Approximately early June 2026 through December 31, 2026

This RFP has been developed by the Independent Research and Science Team and support staff at the Institute for Natural Resources at Oregon State University as part of the Oregon Department of Forestry's Adaptive Management Program.

Available funding is set by the Adaptive Management Policy Committee based on Oregon Board of Forestry approval and is subject to change or rescission.

The Institute for Natural Resources at Oregon State University is the housing agency of the Independent Research and Science Team.

# Table of Contents

Table of Contents	2

Acronyms	4

I.	General Information	5

A.	Introduction	5

B.	Schedule of Dates for Proposal Submission and Review	5

C.	Eligibility Information	5

II.	Overview, Purpose, and Statement of Work	6

A.	Overview and Purpose	6

Adaptive Management Program	6

Background and Project Overview	6

Relevant Documents	8

Purpose	8

B.	Statement of Work	9

Overview of the Specifications of Work	9

Specifications of Work	9

C.	Duration of Grant and General Timeline	12

D.	Funding	12

III.   Full Proposal Submission Guidelines	12

A.	Requested and Required Information for Full Proposal	12

B.	Full Proposal Guidelines	13

B.1 	Title Page	13

B.2 	Proposal Narrative	13

B.3 	Supplemental Information	13

IV.	Proposal Development and Evaluation Process	16

A.	Transparent Review Process and Guidance for Proposers	16

B.	Proposal Development Process	16

C.	Proposal Evaluation Process and Decision Criteria	17

V.	Award Administration Information	18

A.	Notice of Award	18

B.	Award Conditions	18

VI.	Contact	18

Appendix A: AMPC Eastern Oregon Steep Slopes Research Questions Package	19

A. Preliminary research questions	19

B. Research Question Package	19

E.	B.1 The type of research	19

F.	B.2 The rule, biological goals and objectives (BGOs), or other issue being studied	20

“CHAPTER 3. TIMBER HARVEST ON STEEP SLOPES	21

3.2 Goals	21

3.3.8 Timber Harvest on Steep Slopes in Eastern Oregon	22

Appendix B: Species from the HCP that are in Eastern Oregon	23

# Acronyms

AI		Artificial Intelligence

AMP		Adaptive Management Program

AMPC		Adaptive Management Program Committee

CEE		Collaboration for Environmental Evidence

DOI		Digital Object Identifier

HCP		Habitat Conservation Plan

INR		Institute for Natural Resources

IRST		Independent Research and Science Team

NMFS		National Marine Fisheries Service

NOAA		National Oceanic and Atmospheric Administration

OAR		Oregon Administrative Rules

ORS		Oregon Revised Statutes

OSU		Oregon State University

PDF		Portable Document Format

PFA		Private Forest Accord

PI		Principal Investigator

PRISMA	Preferred Reporting Items for Systematic Reviews and Meta-Analyses

RFP		Request for Proposal

URL		Uniform Resource Locator

USFWS		US Fish and Wildlife Service

# General Information

## Introduction

The Institute for Natural Resources (INR), acting on behalf of the Independent Research and Science Team (IRST) for the Oregon Department of Forestry’s Adaptive Management Program, seeks a contractor to undertake a rapid systematic literature review of the evidence and knowledge gaps related to the impact of forest harvesting on hillslope processes and on salmonids and stream-associated amphibians and their habitats in eastern Oregon. A “rapid systematic literature review” is a form of knowledge synthesis that accelerates the traditional systematic literature review process by streamlining or omitting specific, time-intensive methods while maintaining rigorous, transparent, and systematic procedures to identify, select, and critically appraise research.

The IRST anticipates awarding one contract via this request for proposal (RFP). Any contract awarded through this RFP will have a specific timeline for completing the deliverables. The term of the contract is expected to end on December 31, 2026, but may be extended past that date for follow-up questions, etc., upon mutual agreement of the parties.

## Schedule of Dates for Proposal Submission and Review

| Item | Timeline |
| --- | --- |
| Request for proposal (RFP) announced | Monday, February 23, 2026 |
| Written questions submission deadline | Monday, March 2, 2026 |
| Responses to questions posted on website | Friday, March 6, 2026 |
| Full proposals due | Monday, March 23, 2026 (before 11:59 pm Pacific Time) |
| Review period | Approximately March 30 – April 21, 2026 |
| Tentative notice of funding decisions | Approximately late-April |
| Notice to non-awardees | Approximately late-April |
| Award agreement set-up period | TBD |
| Awarded project begins | Approximately early-June |

Note: This timeline is subject to change. Any updates will be posted on Oregon State University’s (OSU) Institute for Natural Resources (INR) IRST Grant Opportunities webpage.

## Eligibility Information

Full proposals may be submitted by any proposer with the capacity, expertise, demonstrated experience, and qualifications to successfully complete the tasks and the deliverables. Proposers must be part of an entity authorized to do business in the State of Oregon. Eligible respondents include, but are not limited to, sole proprietorships, partnerships, limited liability companies (LLCs), corporations, academic institutions, and non-profit organizations. To be considered, the proposer must be registered and in good standing with the Oregon Secretary of State and demonstrate the capability of meeting all insurance and certification requirements outlined in this RFP and the subaward agreement.

IRST members are also eligible proposers. As per Oregon Administrative Rules (OAR) 629-603-0200(6)e, “If an IRST member seeks to respond to an RFP, the IRST shall ensure RFP selections follow conflict of interest standards as established by the Oregon Government Ethics Commission.” Oregon Government Ethics law defines two types of conflicts of interest: actual conflicts of interest (ORS 244.020(1)) and potential conflicts of interest (ORS 244.020(13)).

The project’s lead Principal Investigator (PI) must be deemed eligible by their institution/organization to receive extramural funding, if such funding is pursued. Note: Only one full proposal for each PI may be submitted.

# Overview, Purpose, and Statement of Work

## Overview and Purpose

### Adaptive Management Program

Based on stakeholder negotiations documented in the Private Forest Accord (PFA) Report, the Oregon legislature, in Senate Bill 1501 of the 2022 session, directed the Board of Forestry to update the state’s forest practice rules and establish the Adaptive Management Program (AMP).

The AMP will help design effectiveness monitoring of forest practices rules and inform future rulemaking to support the state’s application for a programmatic habitat conservation plan (HCP), and subsequent incidental take permits from the National Oceanic and Atmospheric Administration (NOAA) Fisheries and the U.S. Fish and Wildlife Service (USFWS). The goal of the program is to use the best available science to assess the effectiveness of rules for achieving the biological goals and objectives described in the HCP. The AMP includes two advisory bodies: (1) the Adaptive Management Program Committee (AMPC), which develops the policy direction for the program, including the research questions; and (2) the IRST, which supports the work of the AMPC by developing research and monitoring options in response to AMPC-developed research question packages, and oversees research and monitoring to address the policy direction.

### Background and Project Overview

- As per Chapter 3 of the PFA Report (Note: the HCP is in preparation and has not been publicly released, and so for the purposes of this RFP “covered species” is defined broadly as salmonids and stream-associated amphibians and their habitats):

- “The goals of the PFA commitments regarding timber harvest on steep slopes is to provide large wood and sediment consistent with maintaining or improving aquatic habitat within large basins over long timeframes. (For the purposes of this Chapter, large basins are those of a size equivalent to those supporting independent populations of Oregon coastal coho salmon. In modeling to support the PFA, these are USGS HUC 4th Field [8-digit] basins). To accomplish this, sediment sources and debris flow runout paths will be identified and a subset of these will be managed during timber harvest activities to retain trees and other vegetation. These actions, together with other HCP commitments, are intended to provide high-quality habitat to support recovery and long-term conservation of the species covered by this HCP on private forestlands.” (p. 31)

- “The PFA does not prescribe new management measures for landslide initiation zones or debris flow traversal channels in eastern Oregon. The PFA authors agree that eastern Oregon’s unique geologies and climates likely mean that these processes are different in magnitude, frequency, and impact on the covered species, when compared to western Oregon. Similarly, the impact of timber harvesting on these processes is potentially different in eastern Oregon. In light of this uncertainty, the PFA authors agree that the Adaptive Management Program examines the scientific literature on the impacts that hillslope processes have on the covered species in eastern Oregon. The primary focus will be on upslope initiated shallow rapid slides and how timber harvesting may impact these in eastern Oregon environments. A secondary and more limited focus is whether other hillslope processes that likely affect covered species are changed by forest practices.” (p. 36)

In Aug 2024, the AMPC research question package pertaining to forest harvesting effects on eastern Oregon mass wasting (Appendix A) was finalized:

Overarching Question: What impact do hillslope processes have on the covered species included in the draft HCP and their habitats in eastern Oregon?

- Primary Focus: What does the literature say about upslope initiated shallow rapid slides and how timber harvesting may impact these in eastern Oregon environments?

- Secondary Focus: Are there hillslope processes other than upslope initiated shallow rapid slides that may affect covered species within the draft Habitat Conservation Plan (HCP) and are these processes changed by forest practices?

Road impacts on shallow rapid slides are not included in the primary and secondary focus questions. These impacts are covered under a separate section of the Forest Practices Act. Similarly, other hillslope processes (e.g. water quality/quantity) unrelated to mass wasting were excluded for the secondary focus question.

Based on these questions, in January 2025, the IRST submitted to the AMPC a research scoping proposal framing how these questions could be addressed using literature reviews, which would assess the robustness of conclusions based on the literature and identify key gaps that might prompt the need for additional research. The IRST conducted a scoping review to characterize the potential amount and nature of the existing relevant scientific literature. It was intended, not as a comprehensive literature review, but as a necessary first step to support the development of a research proposal package to inform the AMPC and Board of Forestry decisions about the utility of soliciting further literature review or research via RFPs.

For the primary focus question, the IRST’s scoping literature review provided a preliminary indication of the existing scientific research available that could potentially determine if shallow rapid slides are an important driver of riparian and stream habitats in eastern Oregon and if forest harvesting is likely to influence characteristics (e.g., initiation rate, size, runout distance) of these slides. The IRST’s scoping literature review used a similar approach for the secondary focus question but considered other potentially important mass wasting processes (deep-seated slides and earthflows, slumping, and sediment bulking associated with debris flows) and the influence of forest harvesting on those processes. Consistent with Appendix A, Section 3.3.8 from the PFA Report, the only hillslope processes considered for the secondary focus question were related to mass wasting.

The Board of Forestry approved the AMPC research agenda, which included this project, in September 2025.

### Relevant Documents

| Document Name | Document Location |
| --- | --- |
| Private Forest Accord Report (2022), Chapter 3 | https://www.oregon.gov/odf/aboutodf/documents/2022-odf-private-forest-accord-report.pdf |
| AMPC’s research questions package (2025) | Appendix A of this RFP |
| IRST’s scoping proposal (2025) | https://ir.library.oregonstate.edu/concern/technical_reports/5d86p7775 |
| Collaboration for Environmental Evidence guidelines (2022) | https://environmentalevidence.org/information-for-authors/ |
| Preferred Reporting Items for Systematic Reviews and Meta-Analyses (PRISMA) Diagram | https://www.sciencedirect.com/science/article/pii/S1743919110000403 |

### Purpose

OAR 629-603-0200(6)(b) authorizes the IRST to develop RFPs in an open, competitive process for research projects in the AMPC-developed research agenda. The 2025 AMPC research agenda calls for a rapid systematic literature review that will inform the extent of knowledge about:

- whether forest harvesting on private lands in eastern Oregon is affecting hillslope processes that in turn may affect salmonids and stream-associated amphibians and their habitats;

- if existing scientific research could potentially determine if shallow rapid slides and complex deep-seated slope failures are prevalent enough to be an important driver of riparian and stream habitats in eastern Oregon; and,

- if forest harvesting is likely to influence characteristics (e.g., initiation rate, size, runout distance) of these slides.

The products and deliverables from this project will be used to evaluate and inform regulation, policy, technical guidance, training as well as identify information gaps. The target audiences for this project are the Adaptive Management Program Committee, the Board of Forestry, the Oregon Department of Forestry, the Oregon Department of Fish and Wildlife, the Oregon Department of Environmental Quality, NOAA, the USFWS, and ultimately Oregon’s citizens.

## Statement of Work

### Overview of the Specifications of Work

The contractor will conduct a rapid systematic literature review about whether and how forest harvesting in eastern Oregon is likely to affect upslope-initiated shallow rapid landslides and associated impacts on salmonids and stream-associated amphibians and their habitats as per the finalized AMPC research questions. A rapid systematic literature review is a form of knowledge synthesis that accelerates the traditional systematic literature review process by streamlining or omitting specific, time-intensive methods to produce evidence-based, actionable information for stakeholders, often completed in several months. It maintains rigorous, transparent, and systematic procedures to identify, select, and critically appraise research, but does so within a compressed timeline. For full contextual information see Appendix A.

This review should summarize the state of knowledge and identify knowledge gaps. The following is a summary of the core elements:

- Meet regularly with the IRST;

- Follow Collaboration for Environmental Evidence (CEE) guidelines and collaborate with the IRST to develop a literature review protocol;

- Conduct the review in accordance with the protocol;

- Analyze the evidence;

- Write a final technical report that documents the search and review process for transparency and replicability, summarizes the state of knowledge, identifies knowledge gaps, and includes summary of findings tables;

- Submit the final report and all supporting documentation, including data; and,

- Participate in an after-action meeting at the end of the project.

Submission of a final report and data as well as conducting the after-action meeting are requirements in OAR 629-603-0200.

### Specifications of Work

The IRST expects the following tasks and deliverables:

Task 1. Project Management

The contractor will coordinate with the IRST to manage this project effectively and efficiently to accomplish this statement of work. The contractor will provide a preferred approach to managing this project, in cooperation with the IRST, that specifies how the contractor will keep the IRST informed of progress on tasks and deliverables and keep the project on time and within budget. In addition to the technical aspects of managing the project, the contractor will engage with the IRST as follows:

- A kick-off meeting to bring the research team and the IRST together to align goals, scope, roles, and timelines.

- Regular interactions with the IRST liaison and INR staff for key decisions/milestones. These interactions may include monthly (or as needed) meetings, email exchanges, or phone calls.

- An after-action review meeting (required in rule) to assess the project’s process, implementation, and intended and actual outcomes to make improvements for future projects.

Task 2.  Conducting the Rapid Systematic Literature Review

A “rapid systematic literature review” process is more streamlined than a traditional, full systematic literature review. As described in CEE guidelines, it:

- Reduces review and inputs (e.g., no external workshops);

- Reduces the number of databases searched and experts consulted;

- Relies on one reviewer, rather than two or more independent reviewers, when screening and extracting information from each publication. However, for this project, a second independent reviewer is required;

- Limits the critical appraisal of study validity;

- Limits the literature database to only relevant documents, rather than including those that were rejected; and,

- Requires no compilation of available empirical datasets.

Activity 2.1. Develop a protocol to conduct the literature review, including the list of questions, eligibility criteria, search strategy, study selection, data extraction, and synthesis method. Relevant, publicly accessible datasets (e.g., DOGAMI landslides database) should also be included in the review by recording metadata in the literature database and including a discussion section about potential utility in the report. The literature should pertain to the effects of forest harvesting on rapid, shallow slides and the effects of such slides on salmonids and stream-associated amphibians and their habitats. The review should include both peer-reviewed and gray literature, although only limited searching for gray literature is expected (no formal surveys, convening of expert focus groups, etc.).

Note: Artificial intelligence (AI)-powered literature searching and synthesis assistants such as Google Scholar Labs, Elicit, Consensus, Scite.ai, Research Rabbit, Connected Papers, and Litmaps could increase the speed and efficiency of science information synthesis. These tools are rapidly evolving and improving but are also novel, with much to be learned about their operation, use, and reliability. If considering such methods, proposers should include in their proposals a discussion of tactics for cross-validation, documentation, and maintaining transparency during development of the review protocol.

"Eastern Oregon" is defined as the region east of the Cascade Crest as described in OAR 629-635-0220. However, the search eligibility criteria should cover slide-prone terrain within a geographic extent that includes similar geographic, geologic, and ecologic environments in the western United States (especially the Rocky Mountain states).

In addition to the primary author, the protocol should include a second independent reviewer and how they would be involved in the screening and coding/analysis of the publications to help reduce bias.

The final search strategy and methodology would be developed in consultation with the IRST.

- Deliverable 2.1a. Written protocol per the above-mentioned components.

Activity 2.2. Perform the literature search according to the protocols.

- Deliverable 2.2a. Bibliographic database, including available studies related to the above thematic area, according to the above-mentioned methods, and containing the following variables (at a minimum): title, authors/institutions, Uniform Resource Locator (URL), Digital Object Identifier (DOI), summary description of the study, and comparators.

- Deliverable 2.2b. Preferred Reporting Items for Systematic Reviews and Meta-Analyses (PRISMA) study flow diagram and table of characteristics of included studies.

- Deliverable 2.2c. A detailed draft systematic literature review report, including a description of the methods (search, data extraction, bias assessment, etc.); synthesis of findings and presentation of the systematic literature review (and meta-analysis, if appropriate), including the use of methods for appraisal of the evidence (including accuracy and precision), descriptive tables of the included studies, summary of findings tables, and review results. The draft report will be reviewed by external reviewers and the IRST. Based on the review comments, a final report will be produced.

Task 3. Final Report

The contractor will produce a narrative final report of the review that synthesizes and summarizes the literature and findings. The final report will include:

- Deliverable 3.1. Final copy of systematic literature review report.

- Deliverable 3.2. Final copies of data.

- Deliverable 3.3. PowerPoint presentation slides, when appropriate.

- Deliverable 3.4. A presentation to the IRST at a regularly planned IRST meeting.

Task 4. After-action Review Meeting

This will be a meeting between the IRST, the contractor, and other cooperators (e.g., ODF, etc.) to assess the project’s process, implementation, and intended and actual outcomes to make improvements for future projects.

## Duration of Grant and General Timeline

The duration of proposed work is estimated to be about 7 months, after the award set-up period. The proposed work is expected to begin by early June 2026. Deliverables, including the final report, are due no later than December 17, 2026.

General Project Milestones

| Milestones | General Timeline |
| --- | --- |
| Kick-off meeting | Within 2 weeks of project start date |
| Interactions with IRST liaison and for key decisions/milestones | Monthly, or as needed |
| Draft technical final report submitted for review and revision process | 2 months before project end |
| Detailed final report*, data*, and all supporting documents submitted to IRST | December 10, 2026 |
| Presentation of project and after-action meeting | December 17, 2026 |
| * Indicates deliverables as defined in rule, OAR 629-603-0200(6)b. |  |

## Funding

The maximum funding request for this competition is $80,000. Grant funding comes from the Oregon Department of Forestry. Available funding is subject to change and rescission.

There is no cost share required for this opportunity.

# III.   Full Proposal Submission Guidelines

Below are details on developing and submitting the full proposal. This guidance, relevant templates and other documents are available on INR’s IRST Grant Opportunities webpage.

Full proposals must be submitted by email to irst-contact@oregonstate.edu by Monday, March 23, 2026, before 11:59 p.m. PT. The email subject line should be “[PI last name], Forest Harvesting-Mass Wasting RFP”. No incomplete or late proposals will be accepted. All provided narrative guidance must be followed. An acknowledgement of receiving the proposal will be sent.

## Requested and Required Information for Full Proposal

A full proposal has three categories of requested and required information:

- Title Page

- Proposal Narrative

- Supplemental Information

NOTE: Principal Investigators at OSU do not need to submit proposals through the Cayuse system.

## Full Proposal Guidelines

Below are details on developing and submitting the full proposal. The full proposal (title page, proposal narrative, and supplemental documents) must be submitted as a single PDF. The proposal budget can be submitted as a separate document (in Excel format).

### B.1 	Title Page

The title page form, which is also available on the IRST Grant Opportunities webpage, must be completed, signed, and submitted as part of the full proposal.

### B.2 	Proposal Narrative

There is a 10-page limit for the narrative. The page limit includes graphs and tables but excludes references and the additional requested/required elements listed below. All pages must be single- or double-spaced, 11- or 12-point font (Calibri, Aptos, Times New Roman, or Arial preferred), and printable on 8.5-inch x 11-inch paper, with 1-inch margins.

The narrative should include the following sections:

- Technical Approach (10-page limit)

The technical approach must describe the proposer’s demonstrated understanding of the project by establishing a clear grasp of the requested tasks and deliverables considering the goals and desired outcomes. The approach must also include a detailed description of how the rapid systematic literature review will be conducted, and how the approach links to the deliverables in the Statement of Work. The proposer should describe any proven systematic approach to completing the work and should articulate the data and methods used in projects of similar scope and complexity as detailed in this RFP. The proposer should also highlight suggestions for tasks and deliverables that could provide enhanced efficiency, i.e., robust deliverables.

- References

Provide those cited in the narrative. Note: This is not part of the 10-page limit.

### B.3 	Supplemental Information

Supplemental information does not count toward the 10-page proposal narrative limit.

- Project Timeline (1-page limit) (required and scored)

Using the tasks, deliverables, and general project milestones in the Statement of Work as a guide, provide a detailed timeline of the team’s proposed strategy and discuss how the success of the project (i.e., objectives, timelines, milestones) and outcomes of the project will be measured and reported.

- Project Management (1-page limit) (required and scored)

Describe how the project will be managed to achieve the project’s outcomes and deliverables.

- Qualifications (required and scored)

Project Team Overview (2-page limit). The proposer should provide a summary of all team members and their roles, including subcontractors and senior management advisors. The proposer should demonstrate that the proposed team members and sub-contractors have the expertise, past performance, and qualifications to handle all aspects of the work to successfully implement the project. The proposer should describe who will fill the role of project manager and demonstrate that the project manager has sufficient and similar experience to ensure the project will be well managed.

Key Persons. Supply curriculum vitae or biosketch for the PI, co-PIs, project manager, and other key persons (2-page limit, each). Biosketches should include information regarding recent projects pertinent to this RFP call.

- Demonstrated Experience (optional)

The proposer may submit one page listing up to five recent projects that demonstrate the key personnel’s experience that are similar to the Scope of Work/Specifications detailed in this RFP. For each project, the proposer should include a brief description of the project and the final deliverable(s), and the name of funder/recipient of the final product(s).

- Budget and Budget Justification (required and scored)

The proposer shall submit a clear, concise, and accurate budget and budget justification that reflect the financial plan for accomplishing the effort contained in the proposal. The proposer shall submit a full budget in sufficient detail so that a determination of reasonableness can be made.

The proposer is also required to provide complete budget justification for each dollar value entered for each project year in the budget for various categories, which may include the following:

Salaries and Wages: Salaries and wages should be detailed by level of effort (i.e., numbers of months, etc.) of each labor category and the applicable labor rate. The source of labor rates shall be identified and verified. For Senior Personnel, list the name, title, and months of salary requested. For other personnel, designate the job title, and provide the name (if possible), full-time monthly salary, and months of salary requested. The proposer should also indicate the role each member will play in the project. Requested person months cannot exceed 100% of any individual’s time.

EXAMPLE

Senior Personnel:

Principal Investigator, [NAME], is requesting [NUMBER] person months of salary at [$X,XXX/mo.] to [DUTIES].

Other Personnel:

- Research Assistant, [NAME], is requesting [NUMBER] person months of salary at [$X,XXX/mo.] to [DUTIES].

- Fringe Benefit: Fringe benefits are specifically identified to each employee and are charged individually as direct costs.

EXAMPLE

Senior Personnel:

Principal Investigator, [NAME], is requesting [$X,XXX] in fringe benefits calculated at [XX%] of their salary.

Other Personnel:

Research Assistant, [NAME], is requesting [$X,XXX] in fringe benefits calculated at [XX%] of their salary.

- Permanent Equipment: List any item with a unit cost of over $5,000 or more and has a useful life of more than one year. List each piece of equipment to be purchased and provide a detailed description of how it will be used in the project. Items that do not meet this definition should be listed under supplies.

- Materials and Supplies: Explain the type of supplies to be purchased and how they will be used. If the supplies cost more than $5,000 or 5% of the award, provide a breakdown of supplies by quantity and cost per unit, if known. Indicate the basis for the estimate of supplies, i.e., historical use on similar projects. In the case of computers, explain how it is related to the project as opposed to having an administrative function.

- Travel: Describe the travel involved, its purpose, and explain how the proposed travel is necessary for successful completion of the project. Where applicable, include details such as mileage rates, estimated travel miles, per diem rates, and lodging rates

- Publication Costs. Briefly describe the publication costs involved. Consider both page charges and reprint costs.

- Other Costs. List all other costs, including subcontracts and personal service agreements, and fees for other services.  List each Other Cost as a separate item.  Describe products/services to be obtained and why they are necessary for the project. Note: A letter of commitment is required from each subcontract source. Please use the letter of commitment template, which is accessible on the IRST Grant Opportunities webpage in the templates section.

- Costs Not Requiring Indirect. Describe all costs listed not requiring indirect (e.g., student tuition) and why they are necessary for the project. List each cost as a separate item. For student tuition, indicate the year and the term.

- Indirect Cost:

  - OSU PIs. The negotiated indirect cost rate is 26%. Indirect cost is applied to all direct costs.

Non-OSU PIs. If the proposer is submitting from an entity other than OSU, use the indirect rate indicated by your institution/organization. This rate is negotiated with the federal government for each institution/organization. Attach the institution’s negotiated rate agreement as part of the full proposal submission.

- Letters of Commitment and Support

- Letters of commitment from each PI and co-PI’s authorized representative (required). Please use the letter of commitment template, which is accessible on the IRST Grant Opportunities webpage in the templates section.

- Letter of commitment from each subaward source (required, if applicable).

- Up to 3 letters of support from project partners or interested parties (optional; encouraged but not required).

All letters should be submitted within the full proposal as one PDF.

# Proposal Development and Evaluation Process

## Transparent Review Process and Guidance for Proposers

The IRST is committed to a fair and transparent review process that addresses both study designs and study reports (OAR 629-603-0400(4)(d)). INR is also providing guidance to PIs on preparing proposals that can be easily blinded by INR after submission (i.e., to facilitate removal of identifying information), if needed:

- Consistent use of names and spelling is encouraged (e.g., use either nickname or full name throughout the proposal package, including budget materials).

- Be mindful when citing resources by the Lead PI and/or Co-PIs. Although this may be helpful for traditional reviews, it may make anonymity difficult to maintain.

## Proposal Development Process

The development and review of proposals is a multi-step process:

- The IRST will conduct a question-and-answer period to help potential proposers better understand the research requirements and policy context, and to ask any clarifying questions. This will occur via an online meeting as well as through the submission of written questions. Responses to written questions will be posted on the IRST RFP webpage.

- Full proposals must be submitted as one single PDF by email to irst-contact@oregonstate.edu by Monday, March 23, 2026, before 11:59 p.m. Pacific Time. The email subject line should be “[PI last name], Forest Harvesting-Mass Wasting RFP”. No incomplete or late proposals will be accepted. All provided narrative guidance must be followed.

- Full proposals will be rigorously reviewed following the process outlined in Section IV.C of this RFP.

- A review panel comprised of an IRST liaison and external reviewers will evaluate the proposals using the review criteria provided below.

- The full IRST will consider these evaluations and select a proposal to recommend for funding.

- The IRST selects the successful proposer, as per 629-603-0200(6)(d).

- Proposers will be informed of final decisions by approximately late April 2026. INR and the IRST reserve the right to negotiate and/or adjust the final grant amount and work plan prior to award, as appropriate and consistent with university policy and funds available.

## Proposal Evaluation Process and Decision Criteria

Proposals that do not follow the guidelines outlined in this RFP will not be evaluated. Each compliant full proposal will be evaluated by a review panel comprised of external peer reviewers and an IRST liaison. The review panel will provide both written comments and a proposal rating using review criteria (C.1.). All written peer reviews will then be provided to the IRST, who will themselves evaluate the proposals and the review panel scores, make a determination, and award the grant. Review panelists’ names will not be directly associated with their individual reviews.

As per rule, those serving on the review panel will be identified. INR will make their names available on its IRST Grant Opportunities webpage.

C.1. Review Criteria and Weight

Proposers should directly and explicitly address the following criteria within their proposal. Each submittal will be rated using a point system, with a total of 100 points possible. Proposals will be evaluated based on the quality and extent to which criteria are addressed; failure to provide applicable information in the proposal will affect the final score:

Specific Project Criteria (maximum total points for this section is 50)

- Relevance: How responsive is the proposal to the RFP criteria?

- Timeline: To what degree can the stated deliverables be completed within the proposed timeline?

- Deliverables: To what degree are the deliverables clearly defined?

- Methodology: To what degree does the project produce an objective, reliable, and extrapolatable product through clear, understandable, and robust methods?

- Technical Merit: To what degree is the proposed project feasibly and technically sound?

- Quality Assurance and Control: How well does the proposed work incorporate quality assurance/quality controls into its approach?

Project Team Qualifications (maximum total points for this section is 25)

- Knowledge: Project team has specialized knowledge in the RFP topic areas.

- Experience: Project team has research or appropriate experience relevant to proposed work.

- Project Understanding: Project team has demonstrated understanding of needed research.

Project Budget (maximum total points for this section is 25)

- Alignment: Project budget is justified and aligned with project goals, deliverables, and milestones.

- Reasonableness: Project supplies, materials, equipment, personnel and other costs are clearly described and reasonable to produce described deliverables.

# Award Administration Information

## Notice of Award

The IRST, via INR, will send a grant award notification email to the PI. After the Lead PI acknowledges receipt of the email and acceptance of the grant award, an official “Notice of Award” will be sent. The Notice will include some or all of the following:

- Period of performance

- Name of the principal investigator

- Dollars committed and/or obligated

- Future year commitments

- Accounting and reporting obligations

- Deliverables

- Payment to awardee

- Special terms and conditions

- General terms and conditions

## Award Conditions

In addition to the Notice of Award, OSU and INR prepare an agreement/contract that fully describes the conditions of the award for signature by all partners. Principal Investigators cannot sign on behalf of their home organization/institution/unit. The project cannot begin until the agreement or contract is fully executed.

# Contact

Questions regarding the application process, funding policy, or research scope should be submitted by email to irst-contact@oregonstate.edu by Monday, March 2, 2026, 12:00 pm Pacific Time. The email subject line should be “QUESTIONS: Forest Harvesting-Mass Wasting RFP”.

Responses to the questions will be placed on the IRST Grant Opportunities webpage by Friday, March 6, 2026.

# Appendix A: AMPC Eastern Oregon Steep Slopes Research Questions Package

# A. Preliminary research questions

The research questions apply east of the crest of the Cascades in Oregon and are to be answered via literature reviews. In addition to articulating an overview of relevant literature, the review should provide an assessment of how robust the conclusions from the literature are and key areas in which additional research may be needed.

Overarching Question:

What impacts do hillslope processes have on the covered species in the draft HCP and their habitats in eastern Oregon?

Primary Focus:

What does the literature say about upslope initiated shallow rapid slides and how timber harvesting may impact these in eastern Oregon environments?

Secondary Focus:

Are there hillslope processes other than upslope initiated shallow rapid slides that may affect covered species within the draft HCP and are these processes changed by forest practices?

# B. Research Question Package

The remainder of this document provides contextual information that details the context for the preliminary research questions, as required by rule. The following are organized per the elements in this rule.

## B.1 The type of research

AMPC response:

This research is of type OAR 629-603-0100(1)(a): “Conduct effectiveness monitoring by assessing the degree to which the rules facilitating particular forest conditions and ecological processes achieve the biological goals and objectives. This assessment may include evaluation of cumulative effects.”

## B.2 The rule, biological goals and objectives (BGOs), or other issue being studied

AMPC response:

The BGOs are listed below with those applicable to these questions highlighted:

“Overarching Goal: Forest practices that support the survival and recovery of the covered species by providing clean, cool, connected, and complex habitats.

Goal 1: Provide clean water and substrate for the covered species.

o Objective 1.1 - Forest practices near streams minimize sediment delivery.

o Objective 1.2 – Slope Retention Areas reduce episodic sediment delivery to fish-bearing streams.

o Objective 1.3 – Road runoff directly to streams is minimized.

o Objective 1.4 – Roads are not a significant source of episodic sediment delivery to streams.

Goal 2: Shade and watershed processes controlling stream temperature provide cool water compatible with the needs of the covered species.

o Objective 2.1 – Forest practices maintain stream shade sufficient to support desired cool water temperatures on fish-bearing streams.

o Objective 2.2 – No-harvest RMAs maintain stream shade sufficient to support desired cool water temperatures for covered amphibians.

o Objective 2.3 – Forest practices near non-fish-bearing perennial streams do not notably increase water temperatures in fish-bearing streams.

Goal 3: Stream network connectivity satisfies freshwater habitat needs for covered species.

o Objective 3.1 – Road crossings on fish-bearing streams are passable by the covered fish species.

o Objective 3.2 – Forest practices maintain the hydrologic continuity of stream-associated wetlands and stream-adjacent seeps and springs to stream habitats.

o Objective 3.3 – Timber harvest maintains stream-associated connectivity in riparian areas along non-fish streams sufficient to support covered amphibians.

Goal 4: Riparian areas function to support complex habitats for the covered species.

o Objective 4.1 – Mature, complex riparian forests are fostered in no-harvest zones of RMAs.

o Objective 4.2 – Forest practices within tree retention areas of RMAs promote delivery of large wood.

o Objective 4.3 – Designated Debris Flow Traversal Areas function to deliver large wood to fish-bearing streams.

o Objective 4.4 – Forest practices maintain stream-associated wetlands and stream-adjacent seep and spring habitat for amphibians.”

The issue being studied is outlined in the PFA Report direction, cited below under context of the research question.

B.3 The objective of the research

AMPC response:

The objective of this research is to inform deliberations about whether rules or other policies are needed regarding timber harvest and other forest practices on steep slopes in eastern Oregon to protect HCP-covered species.

B.4 A brief description of the context of the research question

AMPC response: The following direction was provided in the PFA Report and provides the foundation for these research questions:

# “CHAPTER 3. TIMBER HARVEST ON STEEP SLOPES

# 3.2 Goals

The goals of the PFA commitments regarding timber harvest on steep slopes is to provide large wood and sediment consistent with maintaining or improving aquatic habitat within large basins over long timeframes. (For the purposes of this Chapter, large basins are those of a size equivalent to those supporting independent populations of Oregon coastal coho salmon. In modeling to support the PFA, these are USGS HUC 4th Field [8-digit] basins). To accomplish this, sediment sources and debris flow runout paths will be identified and a subset of these will be managed during timber harvest activities to retain trees and other vegetation. These actions, together with other HCP commitments, are intended to provide high-quality habitat to support recovery and long-term conservation of the species covered by this HCP on private forestlands.

3.2.1 Objectives

Aligned with the overall goals for timber harvest on steep slopes to provide high-quality habitat that supports the recovery, protection, and long-term conservation of covered species on private forestlands, the Authors establish the following objectives under the PFA:

      - Leave trees in Designated Debris Flow Traversal Areas to help create and maintain high-quality habitat in:

        - Type F or Type SSBT streams by delivering large wood and regulating sediment storage and transport.

        - Type N streams by creating shade and cover for amphibians covered under the HCP.

      - Leave trees in Slope Retention Areas to:

        - Reduce timber-harvest-related increases in the frequency and volume of sediment delivered to Type F or Type SSBT streams from mass wasting events.

        - Contribute large wood to Type F or Type SSBT streams.

      - Leave trees on a subset of steep (>70%) slopes immediately adjacent to Type F or Type SSBT streams to:

        - Stabilize these areas.

        - Contribute large wood to Type F or Type SSBT streams.

# 3.3.8 Timber Harvest on Steep Slopes in Eastern Oregon

The Private Forest Accord does not prescribe new management measures for landslide initiation zones or debris flow traversal channels in eastern Oregon. The Authors agree that eastern Oregon’s unique geologies and climates likely mean that these processes are different in magnitude, frequency, and impact on the covered species, when compared to Western Oregon. Similarly, the impact of timber harvesting on these processes is potentially different in eastern Oregon. In light of this uncertainty, the Authors agree that the Adaptive Management Program shall, beginning no later than January 1, 2024, examine the scientific literature on the impacts that hillslope processes have on the covered species in eastern Oregon. The primary focus will be on upslope initiated shallow rapid slides and how timber harvesting may impact these in eastern Oregon environments. A secondary and more limited focus is whether other hillslope processes that likely affect covered species are changed by forest practices. Findings of the Adaptive Management Program on these topics will be presented to the Board of Forestry. These findings should focus primarily on the importance of shallow rapid landslides in eastern Oregon to habitat for the covered species and the potential modification of these processes by forest practices or lack thereof. The report on this primary topic may or may not include recommendations as to desirability and relative importance of potential management measures. In addition, the report should convey whether the secondary review of literature on the effect of forest practices on other hillslope processes merits more thorough consideration by the Adaptive Management Program in light of scientific literature on the connection of these processes to covered species. Nothing in this Report should be read to suggest that any additional eastern Oregon steep slope or other hillslope prescriptions are, or are not, necessary. The timber harvest prescriptions for steep slopes established under Section 3.3.3 of this Chapter for Designated Debris Flow Traversal Areas and under Section 3.3.4 of this Chapter for Designated Sediment Source Areas and Slope Retention Areas do not apply to any private forest ownership class east of the summit of the Cascade Mountains. The timber harvest prescriptions for steep slopes established under Section 3.3.7 Stream Adjacent Failures apply to all private forest ownership classes both west and east of the summit of the Cascade Mountains.”

# Appendix B: Species from the HCP that are in Eastern Oregon

Species from the HCP that are in eastern Oregon:

Chinook Salmon

Steelhead

Sockeye Salmon

Bull Trout

Westslope Cutthroat Trout

Lahontan Cutthroat Trout

Great Basin Redband Trout

Mountain Whitefish

Southern Torrent Salamander

Coastal Giant Salamander

Cope's Giant Salamander

Coastal Tailed Frog.

Note: ODF maintains a regulatory GIS layer of the FPA delineation between eastern and western Oregon.

OAR 629-603-0200 (3)(a)

OAR 629-603-0200(3)(a)(A)

OAR 629-603-0200(3)(a)(B)

The most recent version of the BGOs is in the Dec. 2022 draft HCP. The BGOs will be finalized within the HCP due Dec. 31, 2027.

OAR 629-603-0200(3)(a)(C)

OAR 629-603-0200(3)(a)(D)